## Project Overview
Field | Details
Project Title | AI-Based Aadhaar Document Fraud Detection System
Methodology | Agile Scrum
Sprint Duration | 2 Weeks
Total Sprints | 4
Total Duration | 8 Weeks

## Agile Roles
Role | Responsibility
Product Owner | Defines requirements and priorities
Scrum Master | Manages Agile process and removes blockers
Development Team | AI/ML, OCR, CV, Backend & UI Development

## Product Backlog
Epic ID | Epic Name
EP-1 | Data Collection and Preprocessing
EP-2 | AI-OCR and Document Verification
EP-3 | Fraud Detection using Deep Learning
EP-4 | System Integration and Deployment

## Sprint Details
Sprint | Weeks | Epic | Sprint Goal
Sprint 1 | Weeks 1–2 | Data Collection & Preprocessing | Prepare clean and Azure-compatible Aadhaar data
Sprint 2 | Weeks 3–4 | AI-OCR & Verification | Extract and validate Aadhaar data using OCR
Sprint 3 | Weeks 5–6 | Fraud Detection | Detect forged or tampered documents
Sprint 4 | Weeks 7–8 | Integration & Deployment | Deploy and test integrated system

## Sprint Tasks
Sprint | User Story ID | Task Description
Sprint 1 | US-1 | Collect Aadhaar document images
Sprint 1 | US-2 | Preprocess images and extract metadata
Sprint 2 | US-4 | Integrate Azure or tesseract AI OCR
Sprint 2 | US-5 | Validate extracted Aadhaar fields
Sprint 3 | US-7 | Train deep learning / YOLO models
Sprint 3 | US-8 | Detect forgery and visual tampering
Sprint 4 | US-10 | Integrate OCR and fraud detection
Sprint 4 | US-11 | Deploy models for real-time performance
Sprint 4 | US-12 | Develop UI for testing